| BIHAR STATE POWER GENERATION COMPANY LIMITED Registered Office: 5thFloor, Vidyut Bhawan, Bailey Road, Patna – 800001 A Govt. of Bihar Undertaking, CIN: U40102BR2012SGC018888 RFP No: 01/PR/BSPGCL/2022 # Request for Proposal for Selection of Agency for providing Consultancy services for setting up 200 - 250 MW Solar Power Plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar April 2022 |  |
| --- | --- |

Table of Contents

A.	Disclaimer	4

B.	Request for Proposal (RFP) Details	6

C.	Introduction	7

D.	Scope of Work	8

I.	Phase I	8

II.	Phase II	10

E.	Team Composition	12

F.	Pre-Bid Eligibility Criteria	13

G.	Evaluation of Bids	15

H.	Technical Evaluation Criteria	16

I.	Timeline and Payment Schedule	17

I.	Timeline	17

II.	Payment Schedule	18

J.	Brief Description of the Proposal & its Submission	18

I.	Part I: Techno-Commercial Bid	18

II.	Part II: Price Bid	20

III.	Proposal Submission	20

IV.	BSPGCL's Right to Reject Tender:	20

K.	Bid: Terms & Conditions	21

I.	General	21

II.	Liquidated Damages for Delay in Completion	22

III.	Settlement of Disputes and Provision of Arbitration	22

IV.	Force Majeure	23

V.	Term & Termination	23

VI.	Confidentiality	24

VII.	Indemnification	25

VIII.	Subletting or Transfer of Contract	25

IX.	Purchase/Downloading of Bid Documents	25

X.	Language of the Bid	26

XI.	PRE-BID Discussion:	26

XII.	Effective Date of Contract:	26

XIII.	Period of Engagement:	26

XIV.	Defects Liability Period:	26

XV.	Fees and Charges:	26

XVI.	Taxes and Duties:	27

XVII.	Contract Performance Guarantee (CPG):	27

XVIII.	Validity of Bids	27

XIX.	Brief description of the Selection Process:	28

XX.	Modification & Withdrawal:	29

XXI.	Acceptance of Bids:	29

XXII.	Agreement:	29

XXIII.	Refund of Earnest Money Deposit	29

XXIV.	Forfeiture of EMD	29

XXV.	Others	30

L.	Annexures	35

I.	Annexure A: About Bidder	35

II.	Annexure B: Details of works done as per pre-qualification requirements in providing end to end services for various government / private sector	36

III.	Annexure C: Performa of Letter of Undertaking	37

IV.	Annexure D: Performa Bank Guarantee for Contract Performance	38

V.	Annexure E: Proforma for Bank Guarantee In lieu of Earnest Money Deposit	40

VI.	Annexure F: Approach & Methodology along with Work Plan (Bar Chart with Key Deliverables)	42

VII.	Annexure G: Qualification and the experience of the key personnel proposed to be deployed for the task.	43

VIII.	Annexure H: Format for CV for Proposed Team	44

IX.	Annexure I: Format for the Price Bid (Part II)	45

# Disclaimer

- The information contained in this Request for Proposal document (hereafter referred to as “RFP” or subsequently provided to Applicant(s), whether verbally or in documentary or any other form, by or on behalf of the BSPGCL (hereinafter referred to as Company), or any of its subsidiary or employees or advisors, is provided to Applicant(s) on the terms and conditions set out in this RFP and such other terms and conditions subject to which such information is provided.

- This RFP is not an agreement and is neither an offer nor invitation by the Company to the prospective Applicants or any other person. The purpose of this RFP is to provide interested parties with information that may be useful to them in the formulation of their application for qualification and thus selection pursuant to this RFP. This RFP may not be appropriate for all persons, and it is not possible for the Company, its employees or advisors to consider the objectives, financial situation and particular needs of each party who reads or uses this RFP. The assumptions, assessments, statements and information contained in this RFP may not be complete, accurate, adequate or correct. Each Applicant should therefore, conduct its own investigations and analysis and should check the accuracy, adequacy, correctness, reliability and completeness of the assumptions, assessments, statements and information contained in this RFP and obtain independent advice from appropriate sources.

- Information provided in this RFP to the Applicant(s) is on a wide range of matters, some of which may depend upon interpretation of law. The Company accepts no responsibility for the accuracy or otherwise for any interpretation or opinion on law expressed herein.

- Company, its employees and advisors make no representation or warranty and shall have no liability to any person, including any Applicant or Bidder, under any law, statute, rules or regulations or tort, principles of restitution or unjust enrichment or otherwise for any loss, damages, cost or expense which may arise from or be incurred or suffered on account of anything contained in this RFP or otherwise, including the accuracy, adequacy, correctness, completeness or reliability of the RFP and any assessment, assumption, statement or information contained therein or deemed to form part of this RFP or arising in any way with selection of Applicants for participation in the Bidding Process.

- The Company also accepts no liability of any nature whether resulting from negligence or otherwise howsoever caused arising from reliance of any Applicant upon the statements contained in this RFP.

- The Company may, in its absolute discretion but without being under any obligation to do so, update, amend or supplement the information, assessment or assumptions contained in this RFP. The issue of this RFP does not imply that the Company is bound to select and shortlist Applications and the Company reserves the right to reject all or any of the Applications or Bids without assigning any reasons whatsoever.

- The Applicant shall bear all its costs associated with or relating to the preparation and submission of its Application including but not limited to preparation, copying, postage, delivery fees, expenses associated with any demonstrations or presentations which may be required by the Company or any other costs incurred in connection with or relating to its Application. All such costs and expenses will remain with the Applicant and the Company shall not be liable in any manner whatsoever for the same or for any other costs or other expenses incurred by an Applicant in preparation or submission of the Application, regardless of the conduct or outcome of the Bidding Process.

# Request for Proposal (RFP) Details

| Sr. No. | Particulars | Details |
| --- | --- | --- |
| 1 | E-Tendering Notice no: | 01/PR/BSPGCL/2022 |
| 2 | Name of Work: | Selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar |
| 3 | Method of Selection | Combined Quality Cum Cost Based Selection (CQCBS) -70:30 |
| 4 | E-Bid Portal (website): | https://eproc2.bihar.gov.in |
| 5 | E-Tender Cost: | Non-Refundable Fee of Rs 10,000/- |
| 6 | Bid Processing Fee: | Non-Refundable Fee of Rs 590/- |
| 7 | Earnest money deposit (EMD): | Rs. 01 Lakh |
| 8 | Document downloading/sale date starts: | On 04.05.2022 |
| 9 | Document download/ sale date ends: | Upto 25.05.2022, 13:30 hrs |
| 10 | Pre-Bid Meeting Date: | 13.05.2022 after 11:30 AM |
| 11 | E-Bid submission start date: | 04.05.2022, after 08:00 PM |
| 12 | E-Bid submission end date: | 25.05.2022, upto 04:00 PM |
| 13 | Last date for submission of hard copies of requisite documents: | 26.05.2022, upto 04:00 PM |
| 14 | Opening date of e-bid Part-I (Technical): | On 27.05.2022, after 11:00AM |
| 15 | Date of Presentation on Approach & Methodology and Work Plan | after Techno-commercially qualified bidders will be informed through the web portal https://eproc2.bihar.gov.in/ email, which will be held at BSPGCL headquarter, Patna or online. |
| 16 | Opening date of e-bid Part-II (Financial): | To be notified after Technical Part evaluation through the web portal https://eproc2.bihar.gov.in |
| 17 | Consortium Allowed: | Yes |
| 18 | Sub-Contracting Allowed: | No |
| 19 | Proposal Language: | English |
| 20 | Proposal Currency: | INR |
| 21 | Account Details for E-Tender Cost and Bid Processing | To be deposited online through the web portal https://eproc2.bihar.gov.in |
| 22 | Contact Person for addressing queries & clarifications | Name: Sri Gaurav Kumar Designation: Electrical Executive Engineer (Gen) Address: 5th Floor, Vidyut Bhawan, Bailey Road, Patna - 800001 Phone No: 7260800406 Email id:eeegen2@gmail.com |
| 23 | Contact Person for hard copy submission | Designation: Director (Technical), BSPGCL Address: 5th Floor, Vidyut Bhawan, Bailey Road, Patna - 800001 Email id: dtbspgcl@gmail.com |
| 24 | Proposal Validity Date | 180 days from Proposal Submission Date |

Note:

- Bid shall be accepted through the e-tender portal. Tender issuing authority is not responsible for the delay/downloading of tender document by the recipient due to any problem in accessing the e-tender website. The tender issuing authority is also not responsible for delay in uploading bids due to any problem in the e-tender website.

- BSPGCL reserves the right to reject any or all proposals or cancel the bid without assigning any reason thereof.

# Introduction

- Bihar is one of the fastest growing states in India. The rapid economic growth and infra structural development in the state needs to be supported by a proportionate growth in electricity generation. The current installed including allocated power capacity in Bihar stands at 6660MW (June 2021), with renewable contributing to almost 26% of the total capacity. With its large population and rapidly growing economy, Bihar needs access to clean, cheap and reliable sources of energy. Beside addressing the energy demand and access issue, the renewable energy project would attract employment opportunities and Investments in Bihar.

- Bihar State Power Holding Company Limited (BSPHCL), formerly Bihar State Electricity Board (BSEB) is a state-owned electricity regulation board operating within the state of Bihar in India. BSEB was established in 1958 as a statutory corporation under the Electricity (Supply) Act, 1948. BSEB formally started functioning as 5 companies on 1 November 2012, namely:

Bihar State Power Generation Company Limited (BSPGCL)

Bihar State Power Transmission Company Limited (BSPTCL)

North Bihar Power Distribution Company Limited (NBPDCL)

South Bihar Power Distribution Company Limited (SBPDCL)

Bihar State Power Holding Company Limited (BSPHCL - apex holding company)

- BSPGCL is a Bihar State owned Power Generating Utility incorporated in November 2012 after unbundling of the erstwhile BSEB. Giving the due cognizance to the issue at hand, BSPGCL wants to develop its RE portfolio and accordingly wants to appoint a Consultant for providing consultancy services for setting up 200 -250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar, where approximately 1000-1200 acres of land at each site is under possession of BSPGCL.

# Scope of Work

The scope for the engagement of an Agency for providing Consultancy services for setting up of 200 - 250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar is as follows:

## Phase I

- Preparation of feasibility report for Kajra and Pirpainti separately

- Review of available business Models /route for investment for development of solar power plant with Battery Energy Storage Solution considering land availability, basic infrastructure, evacuation possibilities

- Review of Battery Energy Storage technology landscape

- Assess the ongoing trends and latest developments w.r.t. the deployment of the battery energy storage solutions coupled with RE projects

- Undertake review of international RFPs and identify best practices in RE plus Battery Energy Storage Solution deployment

- Evaluate the state’s current and expected policy scenario / MNRE guidelines by reviewing upcoming regulatory filings, consultations and draft orders

- Identify any policies/incentives in line with each evaluated option

- Prepare tariff projections considering trends in state’s demand supply balance, multi-year tariff regime, tariff design and RPO, SPO requirements by the state

- Submission of feasibility report to evaluate the Capacities & Capital requirements and finalize business model for proposed solar power plant with Battery Energy Storage Solution with details of required regulatory approvals

- Preparation of detailed project report (DPR)for Kajra and Pirpainti separately

- Screening of Available Land: Screening of available land at both the sites using the parameters of land patch size, characteristics, infrastructure availability etc.

- Site Assessment: Assessment of the available site on the parameters of accessibility, land topography and geotechnical conditions, flood risk, water availability, electrical infrastructure, drainage assessment, shading conditions, air pollution etc.

- Solar plant capacity: Based on the land area available and suitable latest technology assessment, consultant shall suggest maximum possible installation capacity of Photovoltaic Solar Power Plant at each site.

- Storage Scoping Study:

- Assist in assessing the demand of the Distribution Companies and assist in sizing of the optimal RE plus battery storage capacity for development

- Review of demand and supply situation for the state distribution companies and assess need for projected peak or RTC RE power, Frequency management, DSM management, etc

- Conduct an integrated resource plan for the state of Bihar to recommend optimal duration of RE based peak/ RTC power

- Make presentation to NBPDCL/SBPDCL/BSPHCL/Procurer(s) to explain the outcome of the scoping study and the identified storage solution (i.e., Peak Management, RTC Power, Frequency management, DSM management) for which the Bid Document shall be drafted.

- Streamline the scoping study with the requirement of the Procurers

- Undertake modelling to determine the optimal capacity of battery storage such that the cost of procurement is minimal for desired energy storage solution

- Project implementation strategy: Consultant shall recommend different methods for implementation of project. An elaborate sequencing of milestones during execution of project shall form part of the report.

- Power Evacuation from the Solar Power plant with Battery Energy Storage Solution: Consultant shall recommend the method of power evacuation after consultations with concerned authorities (viz. STU/CTU/Power Grid/BGCL etc.), along with details regarding evacuation infrastructure available in vicinity of solar power plant with Battery Energy Storage Solution for optimizing the power evacuation. The consultant shall also work out the bill of material along with cost estimate for creation of the required evacuation infrastructure up to the point of sale i.e. at the bus bar of sub-station of the project.

- Solar radiation resource assessment & existing infrastructure: A detailed study of solar radiation resource assessment shall be carried out with other climatic factors such as temperature, wind velocity, precipitation. Availability of water (for cleaning of PV Modules, & domestic purpose of personnel stationed at site) with a suggestion on requirement of water treatment facility based on quality of water available. Site accessibility details, through Rail / Road / Air shall be carried out. Availability of civil/construction raw materials required during development of solar power plant with Battery Energy Storage Solution in the vicinity of respective site has to be worked out by the consultant.

- Technology selection and basic engineering design:  Technologies of PV Modules and Battery Energy Storage Solutions are improving rapidly, and its careful selection will help in lowering the levelized cost of energy (LCOE). Therefore, assessment of the latest and accepted technologies for solar modules and mounting structures, balance of systems components, transformers, cables, protection systems etc. will be carried out by the consultant. Specifications of the various technical components of the solar power plant with Battery Energy Storage Solution infrastructure shall be worked out by the Consultant along with relevant IS/ BIS Codes wherever applicable. Consultant shall also prepare a Good for Construction (GfC) drawings & Bill of Material along with estimated cost of procurement / construction of all the civil, mechanical & electrical infrastructure to be developed for solar power plants with Battery Energy Storage Solution.

- Consultant will indicate the Performance warranties of the plants and mode of performance measurement & penalties to minimize the downtime of the plant

- Project management: Defining roles and responsibilities of Owner, EPC Contractor and Owner’s Engineer for the project and related technologies. Mapping project management techniques and project management

- Legal and Statutory aspects: Identification of clearances and approvals required to be obtained from different Government and Statutory agencies at various stages of development and operation of the project as per the legal framework of Government of India and Government of Bihar

- Plant operation and maintenance: Guidelines for operations and maintenance (O&M) and preventive maintenance of the project, assessment of manpower requirement and facilities to employees

- Social and environmental aspects: Review the existing environmental laws and regulations and report environmental issues that may arise as a result of the implementation of the project. Assessment of social and environmental aspects and their mitigation or prevention during construction and operations of the project. Carry out an assessment from an Environment, Social and Governance (ESG) perspective.

- Project cost estimates and financial details: Review all aspects of the project and prepare a detailed breakup of cost estimate of each component of the project. Financial viability of projects including details of following heads:

  - Various revenue models and estimates of revenue and operating costs

  - Profitability analysis

  - Projected Balance Sheet and Cash flow statement

  - Base Indicators – IRR, DSCR, NPV, etc.

- Risk assessment: Consultant should identify and report potential hazards and risks to be foreseen and its mitigation measures.

- Energy yield assessment: Prediction of energy yields, losses and energy generation probability for the project for the next 25 years

## Phase II

- Vendor Support and Contractual Support separately for Kajra and Pirpainti

- Provide support in bid process management to Bihar State Power Generation Company Limited.

- Preparation of tender document specification covering bid parameters, eligibility and evaluation criteria

- Development of tender document for supply, erection and commissioning of solar power plants with Battery Energy Storage Solution of the estimated capacity as per the DPR for each site at Kajra & Pirpainti in Bihar

- Undertake preliminary discussions with interested Bidders/Financial Institutions/Power Procurer/ other stakeholders to understand optimal contracting conditions, technical requirements, service level agreements, etc.

- Suggest on structuring of the bid document for battery energy storage technology. Consultant shall have to provide pros and cons of adopting RE Storage Application (peak or RTC RE power, Frequency management, DSM management, etc) and their likely impact on the bidding in terms of competitiveness, tariff, regulations, financing etc.

- Participate in pre bid meeting for handling supplier technical queries and issue clarifications in consultation with BSPGCL

- Providing support in evaluating proposals received for the project. This would include assistance in bid evaluation, requesting for clarification, and support in review of bid evaluation report.

- Recommendation on selection of EPC developer for setting up solar power plant with Battery Energy Storage Solution.

- Consultant shall assist BSPGCL in preparation of the final Contract to be signed with the successful Bidder.

# Team Composition

The bidder must possess its core team consisting of manpower details as given herein below:

| Sr. No. | Particulars | Details |
| --- | --- | --- |
| 1 | Engagement Partner: (1 Nos) | - Qualification: Graduate in Engineering with PGDM/MBA - Experience: - 20+ Years of Experience in Power Sector - 15+ Years of Experience in Renewable Sector - Should necessarily have been involved in the selection of at least 2developers for solar projects in India - Should have been involved in preparation of Feasibility Report and DPR for at least 2solar projects in India |
| 2 | Team Leader& Technical Lead: (1 Nos) | - Qualification: Graduate in Engineering with PGDM/MBA - Experience: - 10+ Years of Experience in Power Sector - 8+Years of Experience in Renewable Sector - Should necessarily have been involved in the selection of at least 1 developer for solar project in India - Should have been involved in preparation of Feasibility Report and DPR for at least 1solar project in India |
| 3 | Technical Expert: (1 Nos) | - Qualification: Graduate in Engineering with PGDM/MBA - Experience: - 8+ Years of Experience in Power Sector - 6+Years of Experience in Renewable Sector - Should have been involved in preparation of Feasibility Report and DPR for at least 1solar project in India - Should have been involved in technical analysis, project formulation and implementation for at least 1solar project in India |
| 4 | Bid Process Expert: (1 Nos) | - Qualification: Graduate in Engineering with PGDM/MBA - Experience: - 8+ Years of Experience in Power Sector - 6+Years of Experience in Bid Evaluation, Bid Process etc. - Should necessarily have been involved in the selection of at least 1 developer for solar project in India. |
| 5 | Finance Expert: (1 Nos) | - Qualification: PGDM/MBA or CA - Experience: - 8+ Years of Experience in Power Sector - 6+Years of Experience in advising companies in financial analysis/ modeling and bid evaluation |

Note: Deputation of all the members of the team as given above at BSPGCL/Site is not necessarily required. At least one member out of the Engagement Partner, Team Leader and Technical Expert shall be available at BSPGCL HQ, Patna on all working days.  The other team members maybe called at Patna/Site as per the need/ requirement at short notice.

# Pre-Bid Eligibility Criteria

The Bidder shall be either a single Entity or a Bidding Group or a Bidding Consortium of up to two Entities and may follow any one of the following routes:

    - ROUTE–1 (Sole Bidder/Bidding Company)

Bidder fulfils all the requirements as mentioned hereunder in Qualification Requirement Table (QRT) on standalone basis.

    - ROUTE –2 (Bidding Consortium)

i)	Bidder may be a Bidding Consortium of up to two Entities registered as LLP, Pvt. Ltd., Limited with the Registrar of Companies or Registrar of Firms, societies and chits for the year ending March 31, 2022.

ii)	The members of the Bidding Consortium may collectively meet the requirements of the Technical Criteria as mentioned at Sr. No. 3 of the QRT. However, Bidder on standalone basis should meet Financial Criteria at Sr. No. 2 of the QRT.

iii)	Net worth of all the Consortium members, as on the last date of the last Financial Year out of the three consecutive Financial Years, proposed by Bidder for meeting Technical Criteria, should be positive.

iv)	Both of the Consortium Members will be required to furnish a legally enforceable Consortium Operating Agreement (COA) declaring one of the members as “Lead Member” along with Proposal holding them jointly & severally responsible and liable to BSPGCL to perform all contractual obligations, valid for the entire period of contract. The number of executants of the COA shall not exceed two.

v)	Further the executants of the COA other than the Bidder shall be required to submit an Additional Performance Guarantee equivalent to 1% of the contract value towards the faithful performance of terms & conditions contained in COA as per the format specified in the Bidding documents. This performance guarantee shall be in addition to the Performance Bank Guarantee to be submitted by the Bidder as per Bidding documents and shall be kept valid and operative till the validity of the Performance Bank Guarantee to be submitted by the Bidder.

vi)	In case the Bidder is a Bidding Consortium, drawing technical strength from one of its consortium members in accordance with the provisions of this document, it shall, along with its Project Proposal, submit a legally binding undertaking duly supported by a board resolution of the consortium member fulfilling the technical qualification, that all the technical obligations of the Bidder shall be deemed to be technical obligations of the concerned consortium member fulfilling the technical qualification, and in the event of any default or failure to perform the tender obligation, the said obligation shall be met by the consortium member fulfilling the technical qualification.

vii)	In case a Bidder (whether as a Bidding Company or as a member of the Bidding Consortium or as a Bidding Group) is claiming consultancy/advisory experience of a project where it has provided consultancy as part of a consortium or a joint venture, it shall also submit a notarized copy of its consortium agreement or joint venture agreement (as the case may be), which clearly spells out the extent of its ownership in such consortium or joint venture, as reasonable claim for its qualification, as the case may be.

Bidder may please note that second opportunity may not be given to them for either submission of any clarification, additional information or support document in support of prequalification after opening of tender. Any bid not found to be in conformity with any of the pre-qualifying conditions may be summarily rejected and not be considered for further evaluation.

Qualification Requirement Table (QRT)

| Sr. No. | Particulars | Details |
| --- | --- | --- |
| 1 | Registration: The Bidder should be registered (as LLP, Pvt. Ltd., Limited) with the Registrar of Companies or Registrar of Firms, societies and chits for the year ending March 31, 2022. | Duly attested copies of: a. Certificate of Incorporation, b. Certificate of Conversion to LLP Issued by a. The Registrar of companies b. Registrar of Firms |
| 2 | Financial Criteria (Turnover & Net Worth): a. The Bidder should have a Minimum Average Annual Turnover (MAAT) of at least Rs. 50 Crores per annum during the last three Financial Years ending on 31stMarch for FY 2018-19, 2019-20, 2020-21. b. The Bidder should have a positive Net worth for the all the last three Financial Years ending on 31stMarch 2021. | a. Copy of the audited statement of accounts the last three Financial Years ending on 31-Mar-2021 (P&L Account, Balance Sheet) duly certified by the Chartered Accountant b. Valid Professional Tax Registration. c. Valid Pan Registration & copy of IT Return of last three years. d. Copy of GST Registration |
| 3 | Technical Criteria: The Bidder should have experience of providing consultancy/ advisory services in India for at least ten (10) years and must have provided consultancy services in - minimum three (3) successfully completed Grid Connected Ground Mounted Solar Power Plants of capacities not less than fifty (50) MW; and - minimum one (1) successfully completed Grid Connected Battery Energy Storage Solutions (BESS) of at least five (5) MWh in a single order for Government Entities/Financial Institutions/ Private Sectors in India in last 05 years as on 31.03.2022 | Certificate of Incorporation along with a self-declaration to this effect needs to be submitted on the bidder’s letterhead Work order/Purchase Order/Contract Agreement with completion certificate to be attached as proof |
| 4 | No Blacklisting -The Bidder shall not have been blacklisted from business by any Central Ministries / PSUs / State Govt. Department. -No blacklisting by BSPGCL and its sister or parent companies | a. Self-Declaration from Bidder. b. ‘No blacklisting certificate’ is also to be provided for Debarment/Blacklisting by BSPGCL or any of its sister or parent companies. Notifications issued by one subsidiary of BSPGCL shall automatically extend also to its sister or parent companies. |

Note:

- In case of non-furnishing of any requisite document with the bid, the bid will be considered as non-responsive and bid may be summarily rejected.

- Bidder shall be responsible for all the aspects of defined scope. Also, no further sub-contracting will be allowed during any stage of the project implementation. Suppression of information / facts would lead to instant disqualification.

# Evaluation of Bids

- The Applicant shall be selected under the Quality cum Cost Based System (QCBS) with weightages of 70:30 (70% for technical proposal and 30% for financial proposal) and procedures described in this RFP.

- BSPGCL will evaluate the technical bid first. BSPGCL shall open the “Technical Proposal” only for the bidders who meet the pre-bid eligibility criteria. It will review the technical bids of the short-listed bidders to determine whether the technical bids are as per the requirements laid down. Bids that are not in accordance with the requirements are liable to be disqualified at BSPGCL discretion. Each Technical Proposal will be assigned a technical score out of a maximum of 100 marks. The minimum qualifying score for the technical bid shall be SIXTY-FIVE (65). The financial bids of only those bidders shall be opened whose score is SIXTY-FIVE (65) or above in technical bids.

- BSPGCL will open the financial bid of the technically qualified bidders on e-tender portal whose bids are short listed for financial evaluation. The representatives of technically qualified bidders who want to be present at the opening of financial bid may present themselves.

- The proposal with lowest evaluated cost will be given a financial score of 100 and other proposals given financial scores that are inversely proportional to their prices. The Composite Evaluation would be done as under:

Composite Evaluation (CE):

T: Technical Proposal evaluation score out of 100

F: Financial Proposal evaluation = 100 × Af / Bf

Where, Af= Price of lowest responsive bidder and

Bf= Price of a particular bidder

The Final Total score will be worked out by adding the weighted marks on technical and financial proposals i.e. Final Score of the particular bidder

CE= T*0.70 + F*0.30

- The Bidder securing the highest combined technical and financial score will be awarded the contract/project. Evaluations will be based on documentary evidence submitted by the bidder and presentation before the evaluation committee with respect to evaluation/selection criteria.

# Technical Evaluation Criteria

The Technical Evaluation shall be based on following parameters:

| Sr. No. | Particulars | Details Required | Max. Marks |
| --- | --- | --- | --- |
| 1 | The Bidder providing consultancy/ advisory services in infrastructure sector of India - Tenure of Operation | - ≥10 - <14 Years: 9 Marks - ≥14 - <16 Years: 10 Marks - ≥16 - <18 Years: 11 Marks - ≥18 Years: 12 Marks Certificate of Incorporation | 12 |
| 2 | Experience of Bid Document preparation & evaluation of bids for Solar Power Plant of at least 50 MW capacity in a single order in last 5 years as on 31.03.2022 | Maximum 5 Assignments: 3 Marks Each Work order/Contract Agreement with completion certificate. | 15 |
| 3 | Experience of preparing Detail Project Report for Solar Power Plant of at least 50 MW capacity in a single order in last 5 years as on 31.03.2022 | Maximum 5 Assignments: 4 Marks Each Work order/Contract Agreement with completion certificate | 20 |
| 4 | Experience of preparing Feasibility Report for Solar Power Plant of at least 50 MW capacity in a single order in last 5 years as on 31.03.2022 | Maximum 5 Assignments: 2 Marks Each Work order/Contract Agreement with completion certificate | 10 |
| 5 | Experience of providing consultancy services for successfully completed Grid Connected Battery Energy Storage Solutions (BESS) of at least five (5) MWh in a single order in last 5 years as on 31.03.2022 | Maximum 2 Assignments: 4 Marks Each Work order/Contract Agreement | 8 |
| 6 | Team Experience | As per Team Composition, Qualification and Experience: - Engagement Partner: 3 Marks - Team Leader& Technical Lead: 3 Marks - Technical Expert: 2 Marks - Bid Process Expert: 1 Mark - Finance Expert: 1 Mark Self- certified CV (Refer Annexure-H) | 10 |
| 7 | Approach & Methodology and Work Plan (Techno-commercially qualified bidders will be informed for a presentation on the plan at BSPGCL Headquarter, Patna or online) | It must include the Firm philosophy and Methodology, Scheduling and Time Control Processes, Risk Management, Cost Planning, Monitoring and Control Methodology, Application of appropriate technology, Commissioning methodology and post-construction services etc. | 10 |
| 8 | Average Annual Turnover per annum during the last three Financial Years ending on 31st March 2021. | - ≥50 - <60 Crs: 12 Marks - ≥60 - <70 Crs: 13 Marks - ≥70 - <80 Crs: 14 Marks - ≥80 Crs: 15 Marks | 15 |
| 9 | Total Marks |  | 100 |

Note:

- All (project) experiences submitted for eligibility and evaluation must be supported by Work Orders/ Letter of Award/Letter of Intent/duly executed Contracts with Completion Certificates, clearly indicating the scope and value of the (project) experiences issued by the authority not below the rank of Project in-charge.

- For Ongoing assignments, Work order accompanied by certificate duly signed by the authorized signatory of the bidder for the payment made till the experience period sought by the bidder will be considered.

- The (project) experiences that would be claimed by the Applicant against any criteria both for eligibility as well as for technical evaluation must have been executed as the primary/ lead consultant by the Bidder legal entity submitting the bid for this RFP. Extension work orders on an existing project will not be counted as separate projects.

# Timeline and Payment Schedule

## Timeline

- The timeline for completion of various activities under this contract shall be as indicated in the table below:

- The Bidder is expected to adhere to these timelines. However, Bidder can complete the below mentioned tasks before the scheduled timelines. In case the activities envisaged are not initiated or completed within this timeframe, then the subsequent timelines and effort would be mutually agreed.

- The timeline given below shall be applicable irrespective of the work taken for both Kajra and Pirpainti either separately or together.

| Sr. No. | Key Activities | Timelines |
| --- | --- | --- |
| A | Phase I |  |
| 1 | Inception meeting and project kick-off | Within 1 day of the engagement start date |
| 2 | Submission of Draft Feasibility report | Within 3 weeks from date of engagement start date |
| 3 | Submission of Feasibility report | Within 1week post comments received from BSPGCL on Draft Feasibility report |
| 4 | Submission of Draft DPR | Within 4 weeks post finalization of Feasibility report |
| 5 | Submission of Final DPR | Within 1week post comments received from BSPGCL on Draft DPR |
| B | Phase II |  |
| 1 | Submission of Draft Bid Process and Tender documents | Within 3 weeks of acceptance of DPR from BSPGCL and go ahead from BSPGCL |
| 2 | Submission of Final Bid Process and Tender documents | Within 1 week post comments received from BSPGCL on Draft Bid Process and Tender documents |
| 3 | Bid process completion | Within 3 months post finalization of Bid Process documents |

## Payment Schedule

Payment will be done as per mentioned milestones for Kajra and Pirpainti separately upon submission of the progress reports detailed in ‘Scope of Work’. Payments will be made to the Agency, after raising invoice post milestone achievement, in line with the table mentioned below. The resources will work at Vidyut Bhawan, Patna/project site(s) and it is important that the named Engagement Partner / Team Leader (as well as team) remain available for discussions/ meetings at a short notice.

Payment terms for Kajra and Pirpainti separately with milestones and timelines are shown below:

| Sr. No. | Activity | Payment Milestone | Payment |
| --- | --- | --- | --- |
| 1 | Phase I | Submission of Draft Feasibility report | 10% of contract value |
|  |  | On acceptance of Final Feasibility report | 10% of Contract value |
|  |  | Submission of Draft DPR | 20% of Contract value |
|  |  | On acceptance of Final DPR | 10% of Contract value |
| 2 | Phase II | Submission of Draft Bid Process and Tender documents | 20% of Contract value |
|  |  | On acceptance of Final Bid Process and Tender documents | 10% of Contract value |
|  |  | Techno-commercial evaluation report of bidders | 10% of Contract value |
|  |  | Award of Work to Successful Bidder | 10% of Contract value |

Note: The above-mentioned consultancy fee will be on firm basis and no escalation will be acceptable under any circumstances. All the above payments shall be released to the Sole Bidder/Lead Member in case of Bidding Consortium on receipt of invoices with supporting documents if any, in triplicate by account payee cheque/e-payment subject to statutory deductions of taxes and duties as applicable.

# Brief Description of the Proposal & its Submission

The Bid proposal shall be made in TWO PARTS i.e., PART-I and PART-II. PART-I shall contain the ‘Techno-Commercial Bid' and PART-II shall contain the ‘Price Bid', which shall be prepared in the manner described below:

## Part I: Techno-Commercial Bid

- The following documents duly filled in and signed by the Bidder shall be submitted as PART-I of the Bid Proposal:

  - Full information about the Bidder along with profile of organization as per details shown in enclosed. Annexure: A

  - The Bidder shall submit the documentary evidence in support of all the Pre-Qualification requirements. Annexure: B (For Completed Work)

  - Composition of team personnel and the task which would be assigned to each team member for this project should be attached as per Annexure: G.

  - CV of professionals proposed to be engaged as per Annexure: H

  - Letter of Undertaking including declaration that no employee of BSPHCL or its subsidiary companies or his/her relative(s) is/are partners/directors with the bidding entity, shall be submitted in the prescribed Performa as per Annexure: C.

  - EMD (Rs. 1,00,000/-) in form of Bank Guarantee issued by any Nationalized/ scheduled bank in India in the name of BSPGCL, payable at Patna with validity for eight (8) months from the scheduled date of opening of Techno-commercial Bid. A proforma for Bank Guarantee in lieu of Earnest Money Deposit as per Annexure: E.

  - The Bid document issued by BSPGCL, Amendments / corrigendum / Addendum etc. for the work, if any, duly signed by the Bidder as a token of unconditional acceptance.

  - Interpretations / Clarifications on this Bid document, if any, issued by BSPGCL, duly signed by the Bidder.

  - Audited Profit and Loss Account and Balance sheet along with CA certificate (Turnover and net worth) for the last three financial years are to be enclosed.

  - Copy of the GST registration certificate of the firm.

  - Copy of Permanent Account Number (PAN)/TAN issued by IT department.

  - Approach & Methodology along with Time schedule for completion of work. (Activity-wise bar chart) as per Annexure: F.

  - Declaration by the Bidder on his letter head that firm is not blacklisted by any Central Ministries / PSUs / State Govt. Department/BSPGCL or its sister / parent companies.

  - Power of Attorney in favour of the signatory of the Bidders in original or duly attested by a Notary Public on a non-judicial stamp paper of appropriate value.

  - Bidder has to deposit Rs. 10,000 online through the web portal https://eproc2.bihar.gov.in towards the cost of BOQ.

  - Each page of the Techno-commercial proposal shall be duly signed and stamped by the authorized signatory of the Bidder.

  - Techno-commercially qualified bidders will have to demonstrate a power point presentation on approach & methodology and work plan before BSPGCL authority on scheduled date and time at BSPGCL headquarter, Patna / online which will be informed through the web portal https://eproc2.bihar.gov.in.

  - Any other information, the Bidder desires to furnish in connection with this Bid.

## Part II: Price Bid

- The format for price Bid Performa duly filled-in and Signed by the Bidder shall be submitted as PART-II of the Bid document.

- Bidder shall quote Lump sum fees for Kajra and Pirpainti Separately for the scope of work defined in Bid document for the Selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar. The total sum of quoted Lump sum fees for Kajra and Pirpainti separately shall be considered for financial part evaluation purpose.

## Proposal Submission

- For submission of e-tender through the web portal https://eproc2.bihar.gov.in following procedure shall be adopted by the Tenderer.

  - STEP I:  The Bidder is required to submit the following:

    - Cost of Tender Document (Rs. 10,000) to be paid online through the web portal https://eproc2.bihar.gov.in.

    - EMD (Rs. 1,00,000/-) in form of Bank Guarantee issued by any Nationalized/ scheduled bank in India in favour of Sr. Manager (F&A), BSPGCL, payable at Patna with validity for eight (8) months from the scheduled date of opening of Techno-commercial Bid. A proforma for Bank Guarantee In lieu of Earnest Money Deposit as per Annexure: E.

    - Power of Attorney for submission of Bid.

Note:	The original of Demand Draft/Bank Guarantee for Earnest Money Deposit and the Power of Attorney should be submitted positively one day before scheduled date of opening of Techno-commercial bid to the Director (Tech), BSPGCL.

  - STEP II: All the documents mentioned above alongwith Techno-commercial format duly filled in should be submitted in e-form only as “Part-I – Techno Commercial Bid”.

  - STEP III: "PART-II - Price Bid" shall also be submitted in e-form only in prescribed format duly filled in.

## BSPGCL's Right to Reject Tender:

- BSPGCL reserves the right to reject any or all tenders received at any stage without assigning any reason thereof and the Tenderer shall not be entitled to any costs, charges or expenses in this regard.

- In case Tender/bid is not received within the stipulated time and date as indicated above.

- If the Tender/bid is not accompanied with the requisite tender fee, earnest money deposit, processing fee, requisite documents and schedules.

- If proposal is not a firm proposal.

- If Tenders/proposals is not on the prescribed lines, form and pattern described in the tender document.

- If each page of the proposal (technical and Price) is not duly signed and stamped by the authorized signatory

- If a material misrepresentation is made or discovered.

- If the Bidder does not respond to the BSPGCL asking for supplementary information required for the evaluation of proposal within the given time period.

- If canvassing is found in connection with tenders and/or with uncalled for remarks.

- If the offer is accompanied with any modification(s) and/or special condition(s).

- If the proposal is found with erasing action or overwriting unless the corrections and/or alterations are not accompanied with initials and attestations of the authorized person(s).

# Bid: Terms & Conditions

## General

- BSPGCL reserves its right to issue addendum / Corrigendum to the Bid document prior to opening of Bids. Each Bidder shall acknowledge receipt of the same and attach a copy of addendum / corrigendum along with the Bid after signing and stamping on each page. All addendum /corrigendum shall form part of the Bid document.

- Only authorized representative of the Bidders shall be allowed to attend the Bid opening.

- BSPGCL reserves the right to accept or reject any or all the Bids in whole or part, or to reject the Bid with or without assigning any reasons. Such decisions taken by BSPGCL shall bear no liability whatsoever.

- Rates shall be indicated in figures as well as in words. In case of any discrepancy between the rates in figures and words, the rates in words will prevail.

- The Bidders must sign all pages of the Bid document as per guidelines of Bihar e-procurement portal https://eproc2.bihar.gov.in and should also initial all corrections, if any. Non-compliance shall result in liability for rejection of the Bid.

- The performance of the selected bidder will be reviewed by the authorities of BSPGCL from time to time and if found unsatisfactory, the contract shall be terminated at anytime and CONTRACT PERFORMANCE GUARANTEE (CPG) shall be liable to be forfeited.

- The bidders should have clean and highest standards of professional integrity and ethics and such bidder found under scanner for any misdeeds or under any investigation for misdeeds will be summarily disqualified.

## Liquidated Damages for Delay in Completion

- Time is the essence of the contract. It shall be responsibility of the successful Bidder to whom the contract is awarded, to complete the work within the stipulated period of completion.

- In case the successful Bidders fails to complete the work successfully within the specified period, the bidder shall be liable to pay to the BSPGCL, as liquidated damages and not as a penalty, a sum at the rate of ½ % (Half percent) of the total contract value of the work (as awarded) for every fortnight or part thereof which shall be elapsed between the scheduled time of completion of work and the actual date of completion of work. The total amount of such liquidated damages for delay to be paid under this condition shall not exceed 10% (Ten percent) of the total contract value as awarded.

- The BSPGCL may, without prejudice to any other method of recovery, deduct the amount of such damages from CPG and/or any money which is due or which may become due to the successful bidder under the contract or from any other contract between the successful bidder and the BSPGCL. The deductions of such damages shall not relieve the successful bidder of its obligation to complete the works and demonstrate the performance or any of its other obligations and liabilities under the contract.

- In case of any default on the part of successful bidder at any time during the period of contract, BSPGCL shall be free to cancel the contract and get the work executed through any other agency at the risk and cost of the successful bidder. In the event of such action being taken, the successful bidder shall be liable to Pay for any Loss that the BSPGCL may sustain but he will not be entitled to any gain made by the BSPGCL on account of such default of the successful bidder. The manner and method of taking such action shall be at the entire discretion of the BSPGCL whose decision in the matter shall be final and binding. This right shall be without breach/prejudice to the other rights of the BSPGCL to recover damages for any other breach of the contract by the successful bidder.

- Extension of the Agreement, if required, may be considered beyond contractual period on mutually agreed terms and conditions.

## Settlement of Disputes and Provision of Arbitration

In the event of any dispute such matter or matters giving rise to dispute shall be resolved as outlined below:

- In the event of any dispute, controversy of claim between the parties arising out of the breach, termination or invalidity thereof, the parties shall use their best endeavors to resolve the matter amicably. If the parties are unable to resolve the dispute amicably within thirty (30) days of one party notifying in writing of the existence of the dispute, controversy or claim, either party may serve formal written notice on the other that a material dispute has arisen. If the parties are unable to resolve the dispute within seven (7) days of receipt of such notice, the dispute shall be referred to the Managing Director, BSPGCL for discussion and solution.

- If the aforesaid official could not produce an amicable solution within thirty (30) days of reference, matter shall be referred to the arbitrator for settlement under Arbitration and Conciliation Act 1966. Arbitrator shall be nominated by the Managing Director of the BSPGCL whose decision shall be final and binding on both the parties. Venue of Arbitration will be at Patna. The cost of Arbitration shall be shared by both the parties equally.

- During the pendency of arbitration, no party shall go to the court.

- The jurisdiction of court shall be at Patna for any legal matters.

## Force Majeure

- If, at any time, during the currency of the contract, the performance in whole or in part, by either party is prevented or delayed by war, strike, riot or due to any act of God such as hurricane, flooding, earthquake, volcanic eruption, insurrection, storm, fire which are beyond the control of either party (hereinafter referred to as 'eventualities') then provided notice of the happening of any such eventuality is given by either party to the other within 15 days from the date of occurrence thereof, neither party shall by reason of such eventuality be entitled to terminate this contract nor shall either party have any claim for damages against the other in respect of such non-performance or delay in performance and work under this contract shall be resumed as soon as practicable after such eventuality has come to an end or ceased to exist and the decision of the BSPGCL as to when the work has to be resumed shall be final and conclusive. The time of completion shall then be extended by a period equal to the period during which the eventuality was prevailing. In case of persisting delay of more than three months both the parties may consult each other and arrive at an appropriate decision regarding continuation or otherwise of the contract.

## Term & Termination

- Term: The contract shall be valid as mentioned under Chapter I on both the parties unless terminated earlier pursuant to the Article Force Majeure and Article Termination or extended on the mutually agreed terms and conditions by the parties hereto for a further agreed period.

- Termination of Contract: If, for any reason whatsoever, BSPGCL is unable or unwilling to proceed with the aforesaid works with the successful bidder without any fault of the successful bidder, then BSPGCL shall be entitled to cancel this contract upon giving to the successful bidder fifteen (15) days prior notice in writing in this behalf. In such an event, BSPGCL shall pay to the successful bidder, payment in terms of the payment terms as at Chapter I becoming due to them up to the date of expiry of the period of notice for the actual quantum of work executed by the successful bidder till such period and any liabilities incurred by the successful bidder for due performance of their obligations under this contract up to the date of expiry of the notice. Subject to the above, BSPGCL shall be absolved, in the event of the cancellation of the contract, from liability to pay the balance sum which would otherwise become payable by the BSPGCL to the successful bidder under the terms of Contract.

- BSPGCL will terminate the Contract in case the successful bidder develops conflict of interest and in such an event, the contract will be automatically get terminated and the successful bidder shall have to make good the Cost incurred by BSPGCL on the project along with the fee paid to the successful bidder.

- The termination of contract shall not prejudice or affect the rights or liabilities of the parties accrued or incurred up to the date of such termination.

- In case of delay on the part of the successful bidder in the execution of the works in their scope, affecting the project schedule, for reasons solely attributable to the successful bidder, BSPGCL reserves the right to withdraw that part of the work which is delayed, after giving notice of 15 days in writing to the successful bidder to fulfill that BSPGCL task, failing which they can get the same done by some other agency at the “risk and cost” of the successful bidder (i.e. the successful Bidder to whom the contract is awarded) without prejudice to any other rights and remedies available to BSPGCL under the Contract.

- The above expression “risk and cost” shall include and cover the over and above the contract clause, direct cost incurred in getting such work done through other agency and does not cover the consequential losses or damages, if any, suffered by BSPGCL.

## Confidentiality

- The successful Bidder shall maintain strict confidentiality of all documents, record notes of discussion, drawings, designs and other technical information supplied to them by BSPGCL or prepared by them in respect of the works under this contract and shall not pass on any information to any other agencies/organizations without the written permission of the BSPGCL.

- The successful Bidder shall also take necessary steps to ensure that all persons employed on any work in connection with this assignment have noticed that the Indian Official Secret Act 1923 (XIX of 1923) applies to them and shall continue even after the execution of such work(s) under the contract.

- After completion of works, the successful Bidder should return all relevant documents to BSPGCL.

## Indemnification

The successful bidder assumes responsibility for and shall indemnify and save harmless the BSPGCL from all liability, claims, costs, expenses, taxes and assessments including penalties, punitive damages, attorney’s fees and court cost which are, or may be required with respect to any breach of the successful bidder obligations under the contract, or for which the successful bidder has assumed responsibility under the contract, including those imposed under any contract, local or national laws, or in respect of all salaries, wages or other compensation of all persons employed by the successful bidder in connection with performance of any work covered by the contract. The successful bidder shall execute and deliver such other further instruments and to comply with all the requirements of such laws and regulations as may be necessary thereunder to confirm and effectuate the contract and to protect the BSPGCL. The BSPGCL shall not be in any way held responsible for any accident or damages incurred or claims arising there from during discharge of the obligations by the Consultant under this contract.

## Subletting or Transfer of Contract

The successful bidder shall not sublet, assign or otherwise transfer its rights or obligations under contractor any part of the same to any party without the prior written consent of BSPGCL.

## Purchase/Downloading of Bid Documents

- The tender/bid documents will be available at https://eproc2.bihar.gov.in.The Proposal submitted without the cost of tender document and Earnest Money Deposit will be rejected out rightly.

- Bihar State Power Generation Company Limited reserves right to accept or reject any tender or part and/or accept other than the lowest bid without assigning any reason at any stage in the paramount interest of the Company. The Bidder shall have no claim in this regard whatsoever.

- The cost of Bid document as specified above has to be submitted online through the web-portal https://eproc2.bihar.gov.in. Bids shall be summarily rejected if the stipulated cost of Bid document is not paid as specified above.

- The bidders are required to quote the rate strictly as per the terms & conditions mentioned in the Bid/Tender documents. The conditional Bid/Tender will not be entertained and shall be liable for outright rejection.

## Language of the Bid

All information in the Bid shall be in English. Information in any other language shall be accompanied by its translation in English language. Copy of all documents in English language shall govern.

## PRE-BID Discussion:

Pre-Bid conference/Online Pre-Bid conference will be held on scheduled date. The Bidder may attend the same for discussions/clarifications at their own cost.

Queries of bidder(s), if any, for pre-bid discussion shall be submitted to BSPGCL through email at-least one day in advance.

## Effective Date of Contract:

The date of execution of contract agreement shall be the effective date of contract & time period for completion shall be counted from this date.

## Period of Engagement:

The period of engagement under this contract is NINE (9) MONTHS.

## Defects Liability Period:

The defects liability period for the scope of work defined in this bid document shall be TWELVE (12) MONTHS from the date of successful completion of the works.

## Fees and Charges:

- The Bidder shall quote separate lump sum fees for Kajra and Pirpainti sites for the scope of work defined in this Bid document for the Selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar for the work including tours, travels and accommodation charges, and all taxes & duties as per Price Schedule Format (Part-II of Bid document)

- The fee quoted by the Bidder shall be inclusive of all materials, tools, cost towards net connectivity, laptop and other logistical requirement, duties, levies, taxes including GST, travelling and incidental expenses and all other costs that the consultant may have to incur in connection with works under this contract. No extra charges consequent upon any misunderstanding or otherwise shall be paid by BSPGCL.

## Taxes and Duties:

- Goods & Service Taxes applicable will be quoted as per price format. (Bidder shall indicate the amount and % rate as applicable in the quoted price as per the format of Price Schedule in their Price-Bid)

- All other taxes and duties, if any, are to be included in the quoted lump sum fee.

- Any new taxes levied by the Government and statutory increase on the GST during the tenure of the contract will be reimbursed by the BSPGCL on submission of relevant documentary evidence. However, any reduction in GST, the benefit shall be passed on to the BSPGCL.

- Applicable taxes will be deducted at sources as per statutory requirements. A certificate of TDS will be provided to the successful bidder for the deducted amount.

## Contract Performance Guarantee (CPG):

- The successful bidder is required to submit CONTRACT PERFORMANCE GUARANTEE (CPG) in the form of Bank Guarantee (B.G.) of TEN percent (10%) of the contract value on or before the time of execution of agreement. The Format for B.G. is enclosed at Annexure-D.

- The executant of the Consortium Operating Agreement (COA) other than the Bidder in case of Bidding Consortium shall be required to submit an Additional Performance Guarantee equivalent to 1% of the contract value towards the faithful performance of terms & conditions contained in COA as per the format specified in the Bidding document at Annexure-D. This performance guarantee shall be in addition to the Performance Bank Guarantee to be submitted by the Bidder as per Bidding documents and shall be kept valid and operative till the validity of the Performance Bank Guarantee to be submitted by the Bidder.

- Failure of the successful Bidder to comply with the above requirements of submission of CPG shall constitute sufficient grounds for cancellation of the award of work and forfeiture of EMD.

- No interest shall be payable by the BSPGCL on the CPG.

- Refund of CPG: The CPG shall be returned back to the successful bidder on demand, after the expiry of the defects liability period or on payment of the amount of the final bill payable in accordance with relevant clause of these conditions, whichever is later, provided BSPGCL is satisfied that there is no demand outstanding against the successful bidder.

## Validity of Bids

- The submission of any Bid in accordance with the Bid document and specifications shall constitute an agreement that the Bidder shall have no cause of action or claim, against the BSPGCL for rejection of their Bid. The BSPGCL shall always be at liberty to reject or accept any Bid at its sole discretion and any such action will not be called into question and the Bidder shall have no claim in that regard against the BSPGCL.

- The Bid shall be kept valid initially for a period of six (6) calendar months from the scheduled date of opening of Techno-Commercial Bids.

- In exceptional circumstances, prior to expiry of the original time limit, the BSPGCL may extend the period of validity for a specified additional period. The request will be made in writing to the Bidder.

## Brief description of the Selection Process:

- Two stages selection process will be adopted in evaluating the Proposals. In the first stage, a technical evaluation will be carried out. Based on this technical evaluation, a list of short-listed applicants shall be prepared. In the second stage, a financial evaluation will be carried out. Proposals will finally be ranked according to their combined technical and financial scores. The first ranked Applicant shall be the successful bidder. Second ranked Applicant will be kept in reserve.

  - Part-I of Bids will be opened as per the details given in Tenders: On the due date and appointed time as specified in Tender Document, the BSPGCL will open e-tenders through the web portal https://eproc2.bihar.gov.in. First, Part-I (Techno-Commercial Bids) of all Bids received will be opened in presence of the Bidders or their authorized representatives who choose to attend as per procedure indicated in Tender/Bid Document.

  - After the technical evaluation, BSPGCL would prepare a list of pre-qualified Applicants and Firms. Bids securing a minimum of sixty-five (65) marks shall be considered technically responsive. Such firms shall be declared eligible for opening of their Financial Proposals. A date, time and venue will be notified to all Applicants for announcing the result of evaluation and opening of Financial Proposals.

  - PART-II -PRICE BID OPENING: Before opening of the Financial Proposals, the list of pre-qualified Applicants along with their Technical Score will be read out. The opening of Financial Proposals shall be done through the web portal https://eproc2.bihar.gov.in in presence of respective representatives of Applicants who choose to be present. Bidder’s name, Bid price, the total amount quoted by each Bidder would be announced by the BSPGCL at the time of opening of Price Bid.

- Price Bid evaluation shall be based on the evaluated lump-sum fee as per the Price Schedule subject to correction of errors as per Bid stipulations. In case of any statutory variation in the % rate of GST, from the prevailing rate of 18% (which is prevailing as of April’ 2022), Base Date will be taken as the final due date of Bid submission and % rate of GST will be considered accordingly to arrive at the evaluated lump-sum price. All other stipulation in this regard shall be as per Bid document clause on discrepancies and adjustment of errors and other relevant clauses of Bid document.

## Modification & Withdrawal:

- Bidder may modify or withdraw their Bids after submission in strict adherence to the guidelines of the web portal https://eproc2.bihar.gov.in

- No Bid may be modified or withdrawn after deadline of submission of Bid.

- Withdrawal or modification of a Bid between the deadline for submission of Bids and the expiration of the original period of Bid validity of NIT may result in forfeiture of Bid EMD.

- Bids together with any modification specified under the clause shall be considered as ‘final’ Bid at the time of Opening of Bid.

## Acceptance of Bids:

The successful Bidder shall be intimated about the acceptance of their Bid through email/Speed post/SMS.

## Agreement:

The successful bidder is required to execute an agreement with BSPGCL within 15 days from the issue of Letter of Award (LoA). Bid documents including all enclosures and other correspondences between BSPGCL and the successful bidder including Work Order shall also be treated as a part of the agreement between BSPGCL and the successful bidder for this work.

## Refund of Earnest Money Deposit

- The EMD of unsuccessful Bidders shall be returned within 21 days after award of work order.

- The EMD of the successful Bidder to whom the contract is awarded will be returned after acceptance of work order and receipt of CONTRACT PERFORMANCE GUARANTEEs specified in Bid document.

- In case any Bidder submits the EMD by way of Demand Draft the EMD amount will be refunded by demand Draft only.

## Forfeiture of EMD

- If the successful Bidder fails to submit Contract Performance Guarantees as specified (Annexure - D) within 21 days after the date of issue of work order, then the EMD amount will be forfeited by the BSPGCL, without any notice or proof of damages etc.

- The EMD is liable to be forfeited if :-

- The Bidder modifies or withdraws his offer after due date and time for submission of Bids.

- The Bidder resale from his offer during the validity period.

- The Bidder is revoked during its validity period of the Bid.

- The Bidder increases the prices unilaterally after the opening of Bid and during the validity period of the Bid.

- The Bidder does not accept the correction of Bid price pursuant to 'Discrepancies and Adjustment of Errors', of Bid document.

- The successful Bidder fails to submit the BG towards the Contract Performance Guarantee before the issuance of work order.

- The successful Bidder does not commence the work as specified in Work order.

- The successful Bidder does not submit the duplicate copy of Work Order issued within 15 days from the date of issue as a token of acceptance, unless any other period has been agreed in writing.

## Others

- Canvassing: Canvassing in connection with this Bid is strictly prohibited. Bid of the Bidder, who resorts to canvassing, shall be liable for rejection.

- Bid documents are not transferable: Bid documents are non-transferable and the documents sold by BSPGCL to an intending Bidder shall be used only by that Bidder.

- BSPGCL reserves the right to accept or reject any or all Bids without assigning any reasons thereof. BSPGCL also reserves the right to call for any other details and information from any of the Bidders.

- The Bidder shall enclose a declaration (along with the Bid) to the effect that no employee of BSPHCL or its subsidiary companies or his / her relatives, which term includes wife / husband, parents, grandparents, children, grand-children, brothers, uncles, aunts, cousins and their corresponding in-laws is/are partner(s) with them.

- The Applicants and their respective officers, employees, agents and advisers shall observe the highest standard of ethics during the Selection Process. Notwithstanding anything to the contrary contained in this Bid, BSPGCL shall reject a proposal without being liable in any manner whatsoever to the applicant, if it determines that the applicant has, directly or indirectly or through an agent, engaged in corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice (collectively the “Prohibited practices”) in the selection process. In such an event, the BSPGCL shall, without prejudice to its any other rights or remedies, forfeit and appropriate the performance security, if available, as mutually agreed genuine pre-estimated compensation and damages payable to the BSPGCL for, inter alia, time, cost and effort of BSPGCL, in regard to the work, including consideration and evaluation of such applicant’s proposal.

- Without prejudice to the rights of the BSPGCL under the rights and remedies which BSPGCL may have under the LoA (Letter of Award) or the agreement, if an applicant or consultant, as the case may be, is found by BSPGCL to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice during the Selection Process, or after the issue of the LoA or the execution of the agreement, such applicant or consultant shall not be eligible to participate in any Bid or TENDER  issued by BSPGCL during a period of 2 (two) years from the date of such finding for the applicant or consultant(as the case may be) has been engaged by BSPGCL.

- For the purposes of this Clause, the following terms shall have the meaning here in after respectively assigned to them:

  - “Corrupt practice” means (i) the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of any person connected with the Selection Process (for avoidance of doubt, offering of employment to or employing or engaging in any manner whatsoever, directly or indirectly, any official of the BSPGCL who is or has been associated in any manner, directly or indirectly with the Selection Process or the LOA or has dealt with matters concerning the agreement or arising there from, before or after the execution thereof, at any time prior to the expiry of one year from the date such official resigns or retires from or otherwise ceases to be in the service of the BSPGCL, shall be deemed to constitute influencing the actions of a person connected with the Selection Process; or (ii) save as provided herein, engaging in any manner whatsoever, whether during the Selection Process or after the issue of the LOA or after the execution of the Agreement, as the case may be, any person in respect of any matter relating to the Project or the LOA or the agreement, who at any time has been or is a legal, financial or technical consultant/ adviser of the BSPGCL in relation to any matter concerning the Project;

  - “Fraudulent practice” means a misrepresentation or omission of facts or disclosure of incomplete facts, in order to influence the Selection Process;

  - “Coercive practice” means impairing or harming or threatening to impair or harm, directly or indirectly, any persons or property to influence any person's participation or action in the Selection Process;

  - “Undesirable practice” means (i) establishing contact with any person connected with or employed or engaged by the BSPGCL with the objective of canvassing, lobbying or in any manner influencing or attempting to influence the Selection Process; or (ii) having a Conflict of Interest; and

  - “Restrictive practice” means forming a cartel or arriving at any understanding, or arrangement among applicants with the objective of restricting or manipulating full and fair competition in the Selection Process.

- Conflict of Interest-An Applicant shall not have a conflict of interest that may affect the Selection Process or the Consultancy (the “Conflict of Interest”). Any Applicant found to have a Conflict of Interest shall be disqualified. In the event of disqualification, the Authority shall forfeit and appropriate the Performance Security, if available, as mutually agreed genuine pre-estimated compensation and damages payable to the Authority for, inter alia, the time, cost and effort of the Authority including consideration of such Applicant’s Proposal, without prejudice to any other right or remedy that may be available to the Authority hereunder or otherwise.

- The Authority requires that the Consultant provides professional, objective, and impartial advice and always hold the Authority’s interest’s paramount, avoid conflicts with other assignments or its own interests, and act without any consideration for future work. The Consultant shall not accept or engage in any assignment that would be in conflict with its prior or current obligations to other clients, or that may place it in a position of not being able to carry out the assignment in the best interests of the Authority.

- Without limiting the generality of the above, an Applicant shall be deemed to have a Conflict of Interest affecting the Selection Process, if:

  - The Applicant, its Partners or Directors or Relatives or Associates or consortium member (the “Member”) or Associates (or any constituent thereof) and any other Applicant, its consortium member or Associate (or any constituent thereof) have common controlling shareholders or other ownership interest; provided that this disqualification shall not applying cases where the direct or indirect shareholding or ownership interest of an Applicant, its Member or Associate (or any shareholder thereof having a shareholding of more than 5 per cent of the paid up and subscribed share capital of such Applicant, Member or Associate, as the case may be) in the other Applicant, its consortium member or Associate is less than 5% (five percent)of the subscribed and paid up equity share capital thereof. For the purposes of this Clause, indirect shareholding held through one or more intermediate persons shall be computed as follows:

    - (aa) where any intermediary is controlled by a person through management control or otherwise, the entire shareholding held by such controlled intermediary in any other person (the “Subject Person”) shall be taken into account for computing the shareholding of such controlling person in the Subject Person; and

    - (bb) subject always to Sub-clause (aa) above, where a person does not exercise control over an intermediary, which has shareholding in the Subject Person, the computation of indirect shareholding of such person in the Subject Person shall be undertaken on a proportionate basis; provided, however, that no such shareholding shall be reckoned under this Sub-clause (bb) if the shareholding of such person in the intermediary is less than 26% (twenty six percent) of the subscribed and paid-up equity shareholding of such intermediary; or

    - a constituent of such Applicant is also a constituent of another Applicant; or

    - such Applicant or its Associate receives or has received any direct or indirect subsidy or grant from any other Applicant or its Associate; or

    - such Applicant has the same legal representative for purposes of this Application as any other Applicant; or

    - such Applicant has a relationship with another Applicant, directly or through common third parties, that puts them in a position to have access to each other’s' information about, or to influence the Application of either or each of the other Applicant; or

    - There is a conflict among this and other consulting assignments of the Applicant (including its personnel and other members, if any) and any subsidiaries or entities Controlled by such Applicant or having common controlling shareholders. The duties of the Consultant will depend on the circumstances of each case. While providing consultancy services to the Authority for this particular assignment, the Consultant shall not take up any assignment that by its nature will result in conflict with the present assignment; or a firm which has been engaged by the Authority to provide goods or works or services for a project, and its Associates, will be disqualified from providing consulting services for the same project save and except as provided in Clause10.4.4; conversely, a firm hired to provide consulting services for the preparation or implementation of a project, and its Members or Associates, will be disqualified from subsequently providing goods or works or services related to the same project; or(h) the Applicant, its Member or Associate (or any constituent thereof), and the bidder or Concessionaire, if any, for the Project, its contractor(s) or sub-contractor(s)(or any constituent thereof) have common controlling shareholders or other ownership interest; provided that this disqualification shall not apply in cases where the direct or indirect shareholding or ownership interest of an Applicant, its Member or Associate (or any shareholder thereof having a shareholding of more than 5% (five per cent) of the paid up and subscribed share capital of such Applicant, Member or Associate, as the case may be,)in the bidder or Concessionaire, if any, or its contractor(s) or sub-contractor(s) such Concessionaire or its contractor(s) or sub-contractor(s); provided further that this disqualification shall not apply to ownership by a bank, insurance company, pension fund or a Public Financial Institution referred to in section 4A of the Companies Act,1956.For the purposes of this Sub- clause, indirect shareholding shall be computed in accordance with the provisions of Sub-clause (a) above. For purposes of this TENDER DOCUMENT, Associate means, in relation to the Applicant, a person who controls, is controlled by, or is under the common control with such Applicant, or is deemed or published as an “Associate Office”; or has a formal arrangement such as tie up for client referral or technology sharing, joint venture with the Applicant (the “Associate”); provided, however, that if the Applicant has any formal arrangement such as consortium membership in a consortium of advisers/consultants for a particular assignment/ project, not being this project, with any other person, then such other person shall not be treated to be an Associate of the Applicant solely due to the reason of forming such consortium. As used in this definition, the expression “control” means, with respect to a person which is a company or corporation, the ownership, directly or indirectly, of more than 50% (fifty per cent) of the voting shares of such person, and with respect to a person which is not a company or corporation, the power to direct the management and policies of such person by operation of law or by contract.

- In the event that the Consultant, its Associates or affiliates are auditors or financial advisers to any of the bidders for the Project, they shall make a disclosure to the BSPGCL as soon as any potential conflict comes to their notice but in no case later than 7 (seven) days from the opening of the RFQ applications for the Project and any breach of this obligation of disclosure shall be construed as Conflict of Interest. The BSPGCL shall, upon being notified by the Consultant under this Clause, decide whether it wishes to terminate this Consultancy or otherwise, and convey its decision to the Consultant within a period not exceeding 15 (fifteen) days.

# Annexures

## Annexure A: About Bidder

Name of work:	Selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar

Name of Bidder & Address:

The following information about the company shall be furnished by the Bidder:

| Sr. No. | Description | Particulars |
| --- | --- | --- |
| 1 | Certificate of Incorporation, Certificate of Commencement of Business (in case of Public Ltd. Company) along with the copies of Memorandum and Article of Association are also to be furnished. |  |
| 2 | Nature of business carried on by the company and the provisions of its Memorandum relating thereto |  |
| 3 | Names and including addresses of all the Directors |  |
| 4 | Previous experience of the bidder |  |
| 5 | Its authorized, subscribed and paid up capital as on March 2021 |  |
| 6 | The Annual Turnover of the Company for the last 03 years (Profit & Loss, Balance Sheet and CA Certificate) - 2018-19 - 2019-20 - 2020-21 |  |
| 7 | The Net worth of the Company for the last 3 years (Profit & Loss, Balance Sheet and CA Certificate) - 2018-19 - 2019-20 - 2020-21 |  |
| 8 | Name & Designation of the person who will sign documents, bills and receipts on behalf of the company along with his authorization letter. |  |

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal

## Annexure B: Details of works done as per pre-qualification requirements in providing end to end services for various government / private sector

| Sr No. | Project Details |  |  | Consultancy Works Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Full Postal Address including Tel. Ph. * Fax No. of the client | Name of the Project | Brief Scope of Work | Date of award of work (copy of work order to be submitted) | Scheduled date of completion as per contract | Date of actual completion | Reasons for delay, if any | Date of acceptance by client |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |

Note: The above shall be supported by the copies of the relevant certificates like copies of work orders/Agreements/completion reports etc. from the clients for each work. BSPGCL reserves the right to seek from the Bidder for submission of further Details/information as necessary during evaluation of Bids including TDS certificates in case of works certificates from private organizations.

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal

## Annexure C: Performa of Letter of Undertaking

(To be submitted by the Bidder along with the Bid)

(To be executed on non-judicial stamp paper of suitable value)

Ref: 									Dated:

To,

The Director (Tech.), BSPGCL

Vidyut Bhawan, Patna (Bihar) 800001

Dear Sir,

  - I/We have read and examined the following Bid documents relating to the full scope of work mentioned under selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar.

  - The notice inviting tender for pre-qualifying Conditions of Contract Containing Instructions to Bidder, scope of works, payment terms, and manner of submission of Bid document.

  - I/We here by submit our Bid in terms of NIB/NIT and other documents.

  - I/We undertake to keep our Bid valid initially for a period of 6(six) months from the last date of submission of Bid (i.e. last date up to which Bid is initially kept valid). I/We hereby further undertake that I/We shall not vary/alter or revoke my/our Bid during the said period or extended period if any.

  - I / We also submit herewith the prescribed EMD. BSPGCL shall have the right to forfeit the EMD, if I/We do not comply with the undertaking given at (3) above.

  - Should this Bid be accepted, I/We also agree to abide by and fulfill all the terms, conditions and provisions of the above-mentioned Bid documents.

  - I/We have purchased the Bid document from BSPGCL

  - I / we have visited the site and we are fully acquainted with the local conditions. Our Bid has taken into account the local conditions OR

I / we have not visited the site. However, we un-equivocally confirm that we will not make any claim on the grounds of non-acquaintance with local conditions and factors for execution of the works covered under that Bid documents and technical specifications.

  - I / we hereby declare that no BSPGCL employ or his/her relative is/are Partners/Directors with me/us.

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal

Witness Signature---------------------------

Name & Address ---------------------------

## Annexure D: Performa Bank Guarantee for Contract Performance

(on non – judicial stamp paper of appropriate value)

The non-judicial stamp paper should be in the name of issuing bank

Ref. Bank Guarantee No. 								DATE:

To,

Bihar State Power Generation Co. Ltd.,

Vidyut Bhawan

PATNA (BIHAR)

Dear Sirs,

In consideration of the Bihar State Power Generation Company Limited, (herein after referred to as the `BSPGCL' which expression shall unless repugnant to the Context or meaning thereof include its successors, administrators and assigns) having awarded to M/s._____________________________________with its Registered/Head office at __________________________________ (hereinafter referred to as the Successful Bidder which expression shall unless repugnant to the context or meaning thereof, include its successors, administrators, executors and assigns), a contract by issue of BSPGCL's Work order no . ______________________ dated ____________________ and the same having been unequivocally accepted by the Successful Bidder resulting in a "contract" valued at__________________________ for _________________ (Scope of contract) and Successful Bidder having agreed to provide a contract performance guarantee for the faithful performance of the entire contract equivalent to *_______________% (percent) of the said contract value of the contract to the BSPGCL.

We ___________________________________________________ having (Name and Address)its Head Office at _________________________ (hereinafter referred to as the `Bank', which expression shall, unless repugnant to the context or meaning thereof, include its successors, administrators, executors and assigns) do hereby guarantee and undertake to pay the BSPGCL, on demand any and all monies payable by the Successful Bidder to the extent of____________________________________________ as aforesaid at any time up to________________________________ (days/month/year) without any demur, reservation, recourse or protest and/or without any reference to the Successful Bidder. Any such demand made by the BSPGCL on the Bank shall be conclusive and binding not withstanding any difference between the BSPGCL and Successful Bidder or any dispute pending before any court, tribunal or any other BSPGCL. The Bank undertakes not to revoke this guarantee during its currency without previous consent of the BSPGCL and further agrees that the guarantee herein contained shall continue to been forceable till the BSPGCL discharges this guarantee.

The BSPGCL shall have the fullest liberty without affecting in any way the liability of the Bank under this guarantee from time to time to extend the time for performance of the contract by the Successful Bidder. The BSPGCL shall have the fullest liberty, without affecting this guarantee, to postpone from time to time the exercise of any powers, vested in them or of any right which they might have against the successful bidder, and to exercise the same any time in any manner, and either to enforce or to forbear to enforce any covenants, contained or implied, in the contract between the BSPGCL or any other course of or remedy or security available to the BSPGCL. The Bank shall not be released of its obligations under these presents by any exercise by the BSPGCL of its liberty with reference to the matters aforesaid or any of them or by reason of any other acts of omission or commission on the part of the BSPGCL or any other indulgence shown by the BSPGCL or by any other matters or thing whatsoever which under law would, but for this provision, have the effect of relieving the Bank.

The Bank also agrees that the BSPGCL at its option shall be entitled to enforce this Guarantee against the Bank as a principal debtor, in the first instance without proceeding against the Successful Bidder and notwithstanding any security or other guarantee that the BSPGCL may have in relation the contractor's liabilities.

Notwithstanding anything contained herein above our liability under this guarantee is restricted to ____________________________ and it shall remain in force upto and including________________________** and shall be extended from time to time for such period, as maybe desired by M/s. ________________________ whose behalf this guarantee has been given.

Dated this ____________ day of ________2022 at ___________________.

WITNESS

------------------------- 					Signature ---------------

Signature

-------------------------					 (Bank's Rubber Stamp)

(Name)

--------------------------------------				 (Name) ------------------

Official address

-------------------------------------- 				Designation with Bank stamp

Attorney as per power of Attorney No. --------

Dated ----------------------------

NOTE: *This sum shall be TEN percent (10%) of the contract value in case of Sole Bidder Route. However, it shall be Ten percent (10%) of the contract value by Lead Member and additional One percent (1%) of the contract value by another member of the Consortium in case of Bidding Consortium Route.

** The date will be as specified in the contract.

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal

## Annexure E: Proforma for Bank Guarantee In lieu of Earnest Money Deposit

(Note - To be executed on non-judicial stamp paper of appropriate value)

Bank Guarantee No…………………                                                                         Dt………………

To,

Bihar State Power Generation Co. Ltd.,

PATNA (BIHAR)

Dear Sirs,

In consideration of the Bihar State Power Generation Company Limited, Patna having agreed to accept this Bank Guarantee in lieu of Cash deposit by way of Earnest Money Deposit for due and faithful performance required from M/s…………………………………..……………………….. (herein after referred to as Bidder), the Bank of ……………………………..…..hereby agrees unequivocally and unconditionally to pay within 48 hrs on demand in writing from the Bihar State Power Generation Company Limited, or any officer authorized by it in this behalf or any amount up to and not exceeding Rs………………..……….(in words, Rupees……….…………………………….) to the said Bihar State Power Generation Company Limited, on behalf of the aforesaid M/s………………….………………..who have tendered for the Appointment Of Consulting services for setting up 200-250 MW Solar Power Plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar, India to the said Bihar State Power Generation Company Limited against Tender Specification No…………………..…………….

This agreement shall be valid and binding on this Bank up to and including………………or for such further period as may hereunder be mutually fixed from time to time in writing by the Bihar State Power Generation Company Limited / and the Bidder and shall not be terminable by notice or any change in the constitution of the aforesaid Bank or the firm of Bidders or by any other reasons whatsoever and the Bankers liability hereunder shall not be impaired or discharged by any extensions of time or variations or alteration made, given, conceded or agreed to with or without the Bank’s knowledge or consent by or between the Bihar State Power Generation Company limited and the Bidder in the existing and/ or further tenders and /or contracts.

It is agreed to by the Bank with Bihar State Power Generation Company Limited that if for any reason a dispute arises concerning the Bank’s liability to pay the requisite amount to the Bihar State Power Generation Company Limited under the terms of this Guarantee, the competent court at Patna alone shall have jurisdiction to determine the said dispute and that this shall be without prejudice to the liability of the Bank under the terms of this Guarantee being unequivocal and unconditional as mentioned above.

The liability under this Guarantee is restricted to Rs……………………….(in words Rupees………………………………..……….) only. This Guarantee shall remain in force until……………………….unless a demand to enforce a claim is made under this Bank Guarantee by the Bihar State Power Generation Company Limited to the bank within 6 (Six) months from that date i.e. up to ………., the right of the Bihar State Power Generation Company Limited under this guarantee shall be forfeited and the Bank shall be relieved and discharged from all liabilities there under.

Witnesses:-

1………………………………. (Signature)                                        Signed

…………………………………(Name)                                                for……………

…………………………………(Address)                                             BANK

(Seal)

2……………………………….(Signature)

…………………………………(Name)

…………………………………(Address)

## Annexure F: Approach & Methodology along with Work Plan (Bar Chart with Key Deliverables)

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal

## Annexure G: Qualification and the experience of the key personnel proposed to be deployed for the task.

| Sr. No. | Name of the Key Personnel | Position | Qualification | Experience | Whether working with the firm or hired from outside |
| --- | --- | --- | --- | --- | --- |

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal

## Annexure H: Format for CV for Proposed Team

| Sr. No | Particulars | Details |
| --- | --- | --- |
| 1 | Name of the Person |  |
| 2 | Proposed Position |  |
| 3 | Education Details |  |
| 4 | Whether working with the firm or hired from outside |  |
| 5 | Current Position held in organization |  |
| 6 | Nationality |  |
| 7 | Employability Details (Current to last) |  |
| 8 | Relevant Experience: (Project Wise) |  |
| 9 | Number of years of experience in power & Renewable Sector (separately) |  |
| 10 | Language Proficiency (Excellent, Good, Average & Poo |  |

I self-certify that the above information is true and best to the knowledge of the authorized signatory.

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal

## Annexure I: Format for the Price Bid (Part II)

| Sr. No. | Description of Scope or Work | Quoted Amount in Rs. (Including tours & travels, accommodation, incidental expenses and other taxes & duties etc. excluding GST) |  |
| --- | --- | --- | --- |
|  |  | Rs. In Figure | Rs. In words |
| 1 | Lump sum fees for Kajra for the scope of work defined in Bid document for the Selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plant with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar |  |  |
| 2 | Lump sum fees for Pirpainti for the scope of work defined in Bid document for the Selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plant with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar |  |  |
| 3 | GST (18%) |  |  |
| 4 | Total (1+2+3) |  |  |

Note:

- Rates shall be indicated in figures as well as in words. In case of any discrepancy/ ambiguity, the Rates quoted in words shall be considered as correct.

- GST will be paid as applicable on the date of invoicing and as per actual.

- I hereby certify that the rates quoted above are inclusive of all charges for carrying out consultancy charges for Selection of Agency for providing Consultancy services for setting up 200 -250 MW Solar power plants with Battery Energy Storage Solution at Kajra and Pirpainti locations in the state of Bihar.

Signature

Full Name & Address

Signature of the Tenderer with Date & Seal